## Slide 1
MDIC Open Forum
Quality System Maturity Model Update

## Slide 2: Background / Objective: Quality System Maturity Model
Background
In May 2015, MDIC presented research on current Maturity Models established across various industries and provided recommendations regarding how specific options can be adopted by MDIC stakeholders including, but not limited to, industry members and the Food & Drug Administration.
Objective
As a result of this research, a quality maturity model work stream was formed to develop and implement a Quality System Maturity Model based on the Capability Maturity Model Integration (CMMI) for the medical device industry that is focused on promoting product quality and patient safety.

## Slide 3: Status Report: Quality System Maturity Model 8 Dec 2015
Key Deliverables / Milestones |  |  | 
Milestones / Deliverable | Due Date | Percent Complete | Status
Charter Development | 4 Jun 15 | 100% | 
Develop Pilot Strategy and Approach | 24 Jul 15 | 100% | 
Present updates at CfQ Forum | 8 Sep 15 | 100% | 
Adapt CMMI model and define maturity levels | 24 Sep 15 | 100% | 
Selected pilot process areas built out | 8 Dec 15 | 100% | 
Present Pilot Plan at CfQ Forum | 8 Dec 15 | 100% | 
Identify pilot participants | 31 Dec 15 | 0% | 
Complete Pilot | 31 Mar 16 | 0 % | 
G
Y
R
= On Time
= At Risk
= Late
C
= Complete
Results / Accomplishments
Conducted gap assessment for QSR and ISO Process area selected: Manufacturing Quality Developed preliminary draft of medical profile
Upcoming Activities | 
Activity | Target Date
Identify pilot participants | 31 Dec 15
Determination of resource requirements for Pilot study | 31 Dec 15
Issues/Risks | Actions
Timeline for updating CMMI framework is aggressive | Continuously monitor progress and MDIC will work with CMMI to adapt the framework
C
C
C
C
C
C

## Slide 4: Key milestones and overall project timeline
 | July 2015 |  |  |  | August 2015 |  |  |  | September 2015 |  |  |  | October 2015 |  |  |  | November 2015 |  |  |  | December 2015 |  |  |  | January 2016 |  |  |  | February 2016 |  |  |  | March 2016 |  |  | 
Timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CMMI Pilot Development
Connect with Measures Team
Maturity Model Development
Conduct Pilot
Develop Pilot Strategy and Approach
Identify pilot participants
Present pilot plan at CfQ Forum
Kick-off pilot
Complete pilot
Selection of process areas
Adapt CMMI process framework
Present adapted CMMI Model at CfQ Forum
Selected pilot process areas built out
CMMI alignment and identify gaps/enhancements
Develop plans and on-board pilot participants
Define Maturity levels

## Slide 5
Process Area Selection

## Slide 6: Process Area Selection for Pilot Study
Originally, the selection of focused process area for the pilot study was be based on the following criteria. Scoring would be based on a poll weighting each area.
Ease of Implementation
Process area should be narrow in scope and could easily be implemented in a pilot study
Size Agnostic
Process area should be relevant to small, medium, and large organizations
Alignment to Metrics Team
Process area should align with the Metrics and Measures work stream.
Value to Business
Process area should be of value from a business perspective
Well Defined
Process area should be holistic in terms of people, process, and technology.
Impact on Product Quality
Process area should have a significant impact on patient safety and product quality.

## Slide 7: Regulatory sections were grouped into functional areas
The original approach proved cumbersome. The number of criteria were reduced down to three. Scores were based on the combined averages derived from the original survey. Manufacturing Quality was selected as the process area to be modeled.
Process Area of Quality | Regulatory Sections | Impact on Product Quality | Value to Business | Ease of Implementation | Score
Design Quality | 820.30, 820.35, 830.181 | 10 | 7 | 5 | 7.8
Manufacturing Quality | 820.60, 820.65, 820.70, 820.75, 820.80, 820.86, 820.90, 820.150, 820.160, 820.120, 820.130, 820.181, 820.184 | 9 | 9 | 10 | 9.2
Supply Chain Quality | 820.50, 820.60, 820.65, 820.25, 820.86, 820.90, 820.100, 820.150, 820.160, 820.170, 820.120, 820.130, 820.181, 820.184 | 9 | 8 | 6 | 8.0
Service Quality | 820.200, 820.25, 820.72, 820.60, 820.65, 820.170 | 7 | 10 | 8 | 8.4

## Slide 8
Development of the Model

## Slide 9: Mapping of CMMI Process Framework
The CMMI Framework approximately maps to 80 % of Quality System Regulation and ISO 13485 requirements. Gaps will be filled based on a “Medical Device Profile” to be established moving forward.
30%
40%
20%
50%
10%
80%
90%
60%
100%
CMMI Model
Medical Device Profile
70%
Quality Policy & Practice
All three standards align to the following:
  Management oversight
  Establishment of organizational standards & practices, including V&V
  Monitoring & control
  Training
Medical Device Requirements
Both FDA & ISO incorporate requirements specific to Medical Devices which CMMI does not
Risk Management
FDA and ISO are aligned, but address risk management in separate standards focused on patient impact
CMMI focuses only on project risk
Percent Alignment to QSR and ISO 13485

## Slide 10
Pilot Program

## Slide 11: Benefits of Participation in the Pilot Program
The MDIC Maturity Model Pilot Program is structured to provide inputs into the future state of the overall program, including structuring benefits and receiving early-insights into leading practices.
FDA Interactions
Facilitate direct interactions with the FDA in a non-inspection setting,
Influence over the “next generation” of how the FDA interacts with industry in a more collaborative manner
Provide inputs into the potential regulatory benefits of high maturity. Potentially including reduced pre-market approvals, fewer routine inspections, etc.
Product Visibility
Improvements in overall product quality processes, leading to improved patient safety, customer satisfaction, and operations.
Business Partnering
With a more proactive stance on Quality, a partnership with the business can be developed to utilize Quality as a competitive advantage.
ROI has been proven in companies who have participated in Maturity Model exercises in the past by allowing for quantifiable improvements to be made to the system.
Leading Practice Visibility
Early insight into leading practices across the industry and feedback on how your company aligns to those processes; providing a platform to develop a roadmap for improvements to enhance operations.

## Slide 12: Resources needed for Pilot Program
Assessment
1 Week
MDIC
3 Subject Matter Experts (PT)
1 MDIC Liaison
Leadership for final read-out
1 Assessor
1 FDA Liaison
1 MDIC Maturity Model Core Team Project Manager
Preparation
4 Weeks
Pilot Participants
1 Pilot Liaison (FT) to help facilitate pilot program during assessment and information gathering
MDIC
Need input from those who have participated in assessments previously
1 MDIC Liaison (PT)
1 MDIC Maturity Model Core Team Project Manager (Support
Pilot Participants
Prep meetings to discuss timeline, logistics, and review of any relevant information
1 Pilot Liaison (PT)
Follow-Up
MDIC
1 MDIC Liaison (PT)
1 MDIC Maturity Model Core Team Project Manager (Support)
Pilot Participants
Ad-hoc support from program participants

## Slide 13: Key milestones and pilot project timeline
 | January 2016 |  |  |  | February 2016 |  |  |  | March 2016 |  |  | 
Timeline |  |  |  |  |  |  |  |  |  |  |  | 
Information Gathering (Participants)
Provide on-boarding to key participants
On-Board Pilot Participants
Review and Planning
Select participants
Debrief with participants, FDA, and MDIC
Develop Plan for Next Steps
Review of outcomes
Provide “pre-work” templates and guidance
Conduct alignment and support calls
Conduct Pilot

## Slide 14
Questions?

## Slide 15
Appendix

## Slide 16: Process Area Scoring
 | Rating |  | 
 | High (Score = 3) | Medium (Score = 2) | Low (Score = 1)
Impact on Product Quality | The selected subchapter has a high impact in fulfilling the criterion. For example: Is essential to product quality & safety Has direct impact on product Determines conformance to design or mfg specifications Defines or implements corrective/preventative action for high risk processes or for product. | The selected subchapter has a moderate impact in fulfilling the criterion: For example: Contributes to providing assurance of product quality, but is not fundamental in achieving it. Has indirect impact on product Is one of several non-essential contributing factors | The selected subchapter has little to no impact on product quality.
Well – Defined | The activities required for the selected subchapter are generally well-defined and understood within the industry. There are industry-wide standard practices or recognized standards supporting these activities. The procedural boundaries & scope of activities does not cross multiple functional boundaries. | The activities are expected to be covered by approved procedures; but are typically defined only within individual divisions, sub-divisions or facilities within each organization, and may differ across the industry. The procedural boundaries & scope of activities may cross functional boundaries. | Standard procedures and recognized standards are not established or are in flux. There is no generally agreed upon standards of practice. Implementation is complex and falls across multiple functional boundaries.
Ease of Implementation | Standards and procedures are well-defined and non-complex. Resource requirements are reasonable. Time to implementation is acceptable (< 1 yr) | Standards and procedures are well-defined but may be of increased complexity. Similarly, time & resource requirements may require moderate capital investment. ( 1 - 3 yr) | Standards and procedures may not be well-defined, or are of high complexity. Resource requirements may require extensive time (> 3 yr)

## Slide 17: Process Area Selection
 | Rating |  | 
 | High (Score = 3) | Medium (Score = 2) | Low (Score = 1)
Alignment with Metrics Team | The selected subchapter directly impacts, or is directly measureable in terms of: Design robustness Right first-time production Post-market surveillance | The selected subchapter indirectly impacts: Design robustness Right first-time production Post-market surveillance Inferences with respect to the performance of activities in selected subchapters may be indirectly inferred from any or all of the above metrics. | The activities in the selected subchapter are not related to any of the indicated metrics.
Size Agnostic | The activities in the selected subchapter are not dependent on the size of the organization, in order to be satisfactorily completed. The activity is not labor or resource intensive. | The size of the organization may impact the extent of activities, or the complexity of the technology used. The activity is labor and resource dependent; but labor and resource constraints are not prohibitive to completion. | The activity is heavily dependent on the size of the organization. Activities are highly labor and resource intensive such that only a large organization with significant resources would be capable of implementing these activities robustly
Value to Business | The activities in the selected subchapter contribute directly and positively to the business by generating financial value or significantly reducing costs. | The activities in the selected subchapter do not contribute directly to profitability or cost reduction, but may support such activities; or such activities offer opportunities for incremental improvements. | The activity has little or no impact to profitability and presents little or no opportunity for cost reduction; i.e. is a fixed cost.

## Slide 18: Risk Management
Risk is one area in which the gaps are significant. CMMI, ISO and the QSR all incorporate risk differently, with different emphasis. Risk Management is an area where further alignment may be needed.
CMMI
Project Risk
ISO 14971
Medical Device Risk
FDA Guidance
ICH Q9
CMMI
Risk management is project centric
ISO 14971
Medical Devices
FDA addresses risk for medical devices mainly through guidance documents. It also references ISO 14971
Risk Management
ISO addresses risk for medical devices in a separate standard

## Slide 19: Proposed approach for pilot study
Pilot Study
Develop 1-2 process areas (process areas will be determined based off of selection criteria)
Identify at least 3 companies that will participate in pilot study
FDA will shadow pilot assessment to gain an understanding of how maturity is assessed
Next Steps |  |  | 
Process Area | Model Development | Company Identification | Execution
Selection of the target process area is complete Manufacturing Quality was selected as the functional group to be piloted. Preliminary draft of Medical Device Profile prepared | Definition of maturity levels for process area Complete development of the Industry Profile Amount of resources required Frame out incentives | Reach out to companies to determine interest in pilot study Selection of at least 3 companies | Develop execution plan / schedule for assessors and FDA members Perform maturity model assessment

## Slide 20: High Level Correspondence – QSR, ISO & CMMI
QSR | ISO 14385 | CMMI
B-820.20 Management Responsibility | FDA regulations are highly prescriptive with respect to these areas. ISO does not address these at the same level of detail. | CMMI has no corresponding process area in which to address these.
B-820.22 - Quality Audit |  | 
B-820.25 - Personnel |  | 
C-820.30 - Design Controls |  | 
E-820.50 - Purchasing Controls |  | 
F-820.60 - Identification |  | 
F-820.65 - Traceability |  | 
G-820.70 - General |  | 
G-820.72 - Calibration |  | 
G-820.75 - Process Controls |  | 
H-820.80 - Receiving, in-process, and finished device acceptance |  | 
H-820.86 - Acceptance Status |  | 
I-820.90 - Nonconforming Product |  | 
J-820.100 - Corrective and Preventative Action |  | 
N-820.200 - Servicing |  | 
O-820.250 - Statistical Techniques |  | 
L-820.150 - Handling |  | 
L-820.160 - Storage |  | 
L-820.170 - Distribution and Installation |  | 
M-820.198 - Complaint Files |  | 
D-820.40 Document Controls |  | 
K-820.120 - Device Labeling |  | 
K-820.130 - Device Packaging |  | 
M-820.180 - General Requirements |  | 
M-820.181 - Device Master Record |  | 
M-820.184 - Device History Record |  | 
M-820.186 - Quality System Record |  | 

## Slide 21: Mapping 21 CFR 820 to CMMI
The Maturity model is to be used as maturity assessment tool and NOT as a compliance assessment tool
Sections of 21 CFR 820 Against CMMI Process Areas | Agreement Management | Acquisition Requirements Development | Acquisition Technical Management | Acquisition Verification | Causal Analysis and Resolution | Configuration Management | Decision Analysis and Resolution | Measurement and Analysis | Organizational Process Definition | Organizational Process Focus | Organizational Process Management | Organizational Process Performance | Organizational Training | Process Integration | Process and Product Quality Assurance | Requirements Definition | Requirements Management | Risk Management | Service Continuity | Solicitation and Supplier Agreement Development | Service System Development | Technical Solution | Validation | Verification
Subpart B - Quality System Requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.20 - Management Responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.22 - Quality Audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.25 - Personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart C - Design Controls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.30 - Design Controls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart D - Document Controls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.40 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart E - Purchasing Controls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.50 - Purchasing Controls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart F - Identification and Traceability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.60 - Identification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.65 - Traceability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart G - Production and Process Controls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.70 - General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.72 - Calibration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.75 - Process Controls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart H - Acceptance Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.80 - Receiving, in-process, and finished device acceptance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.86 - Acceptance Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart I - Nonconforming Product |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.90 - Nonconforming Product |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart J - Corrective and Preventative Action |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.100 - Corrective and Preventative Action |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart K - Labeling and Packaging Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.120 - Device Labeling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.130 - Device Packaging |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart L - Handling, Storage, Distribution and Installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.150 - Handling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.160 - Storage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.170 - Distribution and Installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart M - Records |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.180 - General Requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.181 - Device Master Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.184 - Device History Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.186 - Quality System Record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.198 - Complaint Files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart N - Servicing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.200 - Servicing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Subpart O - Statistical Techniques |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
820.250 - Statistical Techniques |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 22: Medical device manufacturing is complex
Diverse and often competing demands must be simultaneously met and have impact across the organization. Any model must incorporate this complexity.
CMMI
Medical Device
Directive
93/42/33d
ISO
21 CFR
820, 801,
803, 806, 812, 814
Canadian
Regulations
SOR 98-282
Quality
Product
Business Objectives & Imperatives
Design & Development

## Slide 23: For a tractable pilot we limit our scope
We focused initially on fewer pieces of the puzzle
CMMI
ISO
21 CFR
820, 801,
803, 806, 812, 814
Canadian
Regulations
SOR 98-282
Quality
Product
Business Objectives & Imperatives
Design & Development

## Slide 24: Closing the Gap
QSR | ISO 14385 | CMMI
B-820.20 Management Responsibility |  | A CMMI profile for Medical Devices is to be created to provide guidance for those areas not well covered by CMMI
B-820.22 - Quality Audit |  | 
B-820.25 - Personnel |  | 
C-820.30 - Design Controls |  | 
E-820.50 - Purchasing Controls |  | 
F-820.60 - Identification |  | 
F-820.65 - Traceability |  | 
G-820.70 - General |  | 
G-820.72 - Calibration |  | 
G-820.75 - Process Controls |  | 
H-820.80 - Receiving, in-process, and finished device acceptance |  | 
H-820.86 - Acceptance Status |  | 
I-820.90 - Nonconforming Product |  | 
J-820.100 - Corrective and Preventative Action |  | 
N-820.200 - Servicing |  | 
O-820.250 - Statistical Techniques |  | 
L-820.150 - Handling |  | 
L-820.160 - Storage |  | 
L-820.170 - Distribution and Installation |  | 
M-820.198 - Complaint Files |  | 
D-820.40 Document Controls |  | 
K-820.120 - Device Labeling |  | 
K-820.130 - Device Packaging |  | 
M-820.180 - General Requirements |  | 
M-820.181 - Device Master Record |  | 
M-820.184 - Device History Record |  | 
M-820.186 - Quality System Record |  | 
The CMMI Medical Device Profile

## Slide 25: The Medical Device Profile will continue to evolve
A comprehensive guideline for the medical device industry should incorporate the full range of regulation and business processes. Ultimately a medical device maturity model must be broad enough to reflect the breath of activities engaged in by the business, above and beyond regulation.
Business Objectives
Patients
Product Quality
Regulations
CMMI