## Slide 1: IM/IT Capital Investment Branch of the OCIO
May 2015
IM/IT Capital Project Management

## Slide 2: The proposed project management tools are aligned with PMI’s PMBOK knowledge areas
Project Management Tools | PMI’s PMBOK Knowledge Areas (management) |  |  |  |  |  |  |  |  | 
 | Integration | Scope | Time | Cost | Quality | Human Resource | Communications | Risk | Procurement | Stakeholder
Project Charter | × | × |  |  |  |  |  |  |  | 
Project Management Plan | × | × |  |  |  | × | × | × | × | ×
Master Plan (Gantt Chart) |  |  | × | × |  |  |  |  |  | 
Resource Plan |  |  |  |  |  | × |  |  |  | 
Organization Change Management Plan |  |  |  |  |  | × |  |  |  | 
Communication Plan and Tracker |  |  |  |  |  |  | × |  |  | 
Quality Management Plan |  |  |  |  | × |  |  |  |  | 
Deliverable Log |  | × |  |  |  |  |  |  |  | 
Personal and Confidential Management Plan |  |  |  |  | × |  |  |  |  | 
Training Log |  |  |  |  |  | × |  |  |  | 
Kick-off Meeting Template | × |  |  |  |  |  |  |  |  | 
Project Status Report | × |  |  | × | × |  | × |  |  | 
Issue Log | × |  |  |  |  |  |  |  |  | 
Risk Log |  |  |  |  |  |  |  | × |  | 
Deliverable Overview and Acceptance Form |  | × |  |  |  |  |  |  |  | 
Change Request Log | × | × |  |  |  |  |  |  |  | 
Action Item Log | × |  |  |  |  |  |  |  |  | 
Decision Log | × |  |  |  |  |  |  |  |  | 
Phase-end Review Report and Project Closure Report | × |  |  |  |  |  |  |  |  | 
Notes: Call out: this doesn’t sufficiently show how to scale tools –
We still need to figure out how to show that

## Slide 3: Ministry, OCIO, DMCTT and TB have different roles and responsibilities across phases of the IM/IT investment lifecycle
Phase | Action / Decision | Organizations / Committees |  |  | 
 |  | Ministry | OCIO | DMCTT | TB
Project Monitoring and Reporting | Ensure project management activities are executed at the project and program levels | R/A/C | I | I | -
 | Provide accurate status reporting and highlight the areas of risk | R/A | C | I | -
 | Conduct periodic review of projects against risk criteria | - | R/A | I | -
 | Conduct third-party review of projects | R | A | I | -
 | Authorize phase-to-phase funding gates | C | R | A | I
 | Review and approve change requests | - | R | A | I
C = Consulted
Person who needs to provide feedback and contribute to the activity
A = Accountable
Person who is ultimately accountable and has decision making and veto power
I = Informed
Person who needs to know of the decision or action
Legend
R = Responsible
Person who performs an activity or does the work
Notes: 3) Identifying areas of risk – reporting and insights regarding project status
Project reviews relative to project risk or to help manage
Ensure project aligns with overall outcomes
Ensure project management activities and templates are executed at project and program level
Adding their party reviews

## Slide 4: A suite of project management tools and templates have been developed to provide a common baseline set of tools
Project management tools have been identified for three generic project phases (Plan, Manage and Close) to enable alignment with multiple methodologies
The list of tools are consistent with PMI’s PMBOK® Methodology
Recognizing projects vary, the recommended use of each tool has been based on the project’s complexity rating as either:
  M: Mandatory – the tool is required for the project
  A: Advised – the tool is advised for the project
  O: Optional – the tool is considered optional for the project
While not all tools will be used for all projects (due to different complexity profiles), it is expected that PMs will consult the project sponsor and exercise their own professional judgment to determine both:
    The applicability of each tool, and
    The level of detail required for each tool
It is anticipated that the PM may choose to develop modified versions of the tools, that still meet the core requirements as outlined in this document, by creating either:
Separate, standalone plans or logs for the largest, most complex projects or
Combining logical documents for smaller, lower complexity projects (i.e. the Project Management Plan could contain the Risk, Resource, Communications, etc. Plans)
The tools required specifically for the long term operations (maintenance) phase have not been explicitly developed; however, many of the tools can be adopted for this phase
Overview

## Slide 5: Sample project management templates and or checklists have been developed for Plan, Manage and Close phases of a project
LOREM IPSUM This is dummy text it is not here to be read. This is dummy text it is not here to be read. This is dummy text it is not here to be read. This is dummy text it is not here to be read. This is dummy text it is not here to be read.
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr
Sales | 0.4 | 0.2 | 0.4
Project Management Tools & Templates
1. Plan
2. Manage
3. Close
Project Status Report
Issue Log
Risk Log
Deliverable Overview and Acceptance Form
Change Request Log
Action Item Log
Decision Log
Project Charter
Project Management Plan
Master Plan
Resource Plan
Organizational Change Management Plan
Communication Plan & Tracker
Quality Management Plan
Deliverable Log
Personal & Confidential Information Plan
Training Log
Kick-off Meeting Template
Phase-end Review Report and Project Closure Report

## Slide 6: Sample1 of project management tools developed for three phases of a project: Plan or initiate or plan; Manage or execute; Close
Plan or Initiate
Manage or Execute
Close
1
2
3
1 | Project Charter
2 | Project Management Plan
3 | Master Plan (Gantt Chart)
4 | Resource Plan
5 | Organizational Change Management Plan
6 | Communication Plan and Tracker
7 | Quality Management Plan
8 | Deliverable Log
9 | Personal and Confidential Information Management Plan
10 | Training Log
11 | Kick-off Meeting Template
12 | Project Status Report
13 | Issue Log
14 | Risk Log
15 | Deliverable Overview and Acceptance Form
16 | Change Request Log
17 | Action Item Log
18 | Decision Log
19 | Phase-end Review Report and Project Closure Report
1 The tools presented here are the most common tools and templates. Depending on the scope of the project, additional project management tools might be required. Refer to your project’s governing project management methodology (i.e. PMI’s PMBOK) for additional guidance.
Project Phases
Notes: Call out: this doesn’t sufficiently show how to scale tools –
We still need to figure out how to show that

## Slide 7: Project management tools1 are scalable depending on the project’s complexity rating established through the Classification Framework
Phase | # | Tool Name | Project Complexity Rating |  | 
 |  |  | Low Complexity | Moderate Complexity | High Complexity
Initiate or Plan | 1 | Project Charter | One document combined |  | 
 | 2 | Project Management Plan |  |  | 
 | 3 | Master Plan (Gantt Chart) |  |  | 
 | 4 | Resource Plan |  |  | 
 | 5 | Organization Change Management Plan | One document combined |  | 
 | 6 | Communication Plan and Tracker |  |  | 
 | 7 | Quality Management Plan | Can be part of the Project Management Plan |  | 
 | 8 | Deliverable Log | - | - | 
 | 9 | Personal and Confidential Management Plan | If applicable |  | 
 | 10 | Training Log | - | - | 
 | 11 | Kick-off Meeting Template | - | - | 
Execute or Manage | 12 | Project Status Report |  |  | 
 | 13 | Issue Log | Can be combined into one document |  | 
 | 14 | Risk Log |  |  | 
 | 15 | Deliverable Overview and Acceptance Form |  |  | 
 | 16 | Change Request Log | - |  | 
 | 17 | Action Item Log | Can be combined into one document |  | 
 | 18 | Decision Log |  | - | 
Close | 19 | Phase-end Review Report and Project Closure Report | - | - | 
1 While not all tools will be used for all projects, the PM is responsible for determining, in consultation with the project sponsor and OCIO, the applicability and detail level required for each tool
Notes: Call out: this doesn’t sufficiently show how to scale tools –
We still need to figure out how to show that

## Slide 8: Project Charter and Project Management Plan are mandatory documents fundamental for defining the ‘what’ and ‘how’
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Initiate or Plan | 1 | Project Charter | The Project Charter documents the vision, goals and expected benefits of the project, as well as the project approach, end-product scope, project schedule, constraints and dependencies, and other important information The Project Charter identifies project leadership and initial stakeholders and provides the formal authorization for the project to proceed | The Project Charter is the source for authorizing the project and documenting key aspects of the project at its inception Once it is approved by the stakeholders, the original charter will not change without agreement by all parties involved | M
 | 2 | Project Management Plan | The Project Management Plan documents the resources and processes that will be used to execute the project The Project Management Plan documents the project organization, work plan approach, deliverable management and project controls, resource plan, project tools, communications, and stakeholder engagement plans | The Project Management Plan communicates how the project will be successfully delivered by the project team and should maintained throughout the life of the project It is a living document and should be considered the primary source for information about the project | M
M: Mandatory
A: Advised
O: Optional

## Slide 9: The Master Plan and Resource Plan are mandatory documents for the planning phase of IM/IT projects
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Initiate or Plan | 3 | Master Plan | The Master Plan represents the project’s schedule; typically in a Gantt Chart format This plan is developed at the same time as the Work Plan, which is the detailed schedule for the project or phase (commonly in Microsoft Project) It also serves as direct input into the project’s Resource Plan | The Master Plan represents the high-level schedule for the project, including major activities and key milestones The Master Plan must be regularly maintained to be current and align with the project’s Work Plan | M
 | 4 | Resource Plan Checklist | The Resource Plan Checklist provides the outline for a full Resource Plan, which provides the planning and management of human resource requirements The Resource Plan confirms project team resource needs, identifies candidates and selects appropriate individuals to fill open project team roles It is updated ahead of each project phase, focusing on the project team needs and new resource needs for the next or upcoming phase | Human resources are required to produce the project deliverables and complete the work, and this plan highlights how to identify resource needs and acquire the resources This plan is used to identify the quantity and type of resources (by skillset) required to deliver the project | M
M: Mandatory
A: Advised
O: Optional

## Slide 10: Organizational Change Management Plan and Communication Plan are mandatory documents for the planning phase of IM/IT projects
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Initiate or Plan | 5 | Organization Change Management Plan | The Organizational Change Management Plan is the plan to describe how the adoption and sustainability of the organizational change will be achieved | The Change Management Plan identifies the necessary activities to drive change in the organization, including stakeholder engagement, leadership alignment, communication, and training and knowledge transfer activities designed to address the needs of different stakeholder groups | M
 | 6 | Communication Plan Tracker | The Communication Plan determines the overall communication approach and guides the development and execution of communication with different stakeholder groups across the project The Communication Plan Tracker is used to track communication activities | The communication plan supports coordination and timely communication of key messages to stakeholders throughout the project The Communication Plan is developed based on the Change Management and Communication Strategies and can be a section within the Organizational Change Management Plan | M
M: Mandatory
A: Advised
O: Optional

## Slide 11: Quality Management Plan and Deliverable Log are advised; Personal and Confidential Management Plan is optional
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Initiate or Plan | 7 | Quality Management Plan | The Quality Management Plan defines the project’s overall quality program objectives, as well as specific plans for quality assurance, quality control, and quality support | The Quality Management Plan describes how the project will deliver work at the desired level of quality and describes how quality management will be executed for the project | A
 | 8 | Deliverable Log | The Deliverable Log defines the complete list of deliverables for a project, and includes the key steps for deliverable review, sign-off and formal acceptance It can be created at the beginning of a project and or iterated as planning for subsequent phases is completed; regardless of development, the log should provide one comprehensive record for the entire project | The Deliverable Log tracks deliverable progress and provides visibility of the progress of every deliverable through to completion NOTE: this log is explicitly linked to the Deliverable Overview and Acceptance Forms for each deliverable | A
 | 9 | Personal and Confidential Management Plan | The Personal and Confidential Management Plan develops and documents the strategy for managing and safeguarding sensitive data It serves as standard operating procedure for the team with respect to data elements, access procedures, transfer, storage, retention and destruction, safeguards, on-boarding, and off-boarding | This plan is required for projects that deal with sensitive information NOTE: This is additional to any and all existing policies and procedures for sensitive data management; projects must fully comply with existing policies at all levels of gov’t. | O
M: Mandatory
A: Advised
O: Optional

## Slide 12: The Training Log and Kick-off Deck are optional documents for the planning phase of IM/IT projects IM/IT projects
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Initiate or Plan | 10 | Training Log | The Training Log documents the courses or learning activities that will be delivered for project team resources to acquire the required project skillsets The Training Strategy can be a sub-section of the Change Management Plan or can be a standalone document The Training Plan is developed based on the Training Strategy and is tracked in the Training Log | The Training Log tracks the training progress | O
 | 11 | Kick-off Meeting Template | The project kick-off is a presentation delivered in the start-up phase to provide project stakeholders with an overview of the project. It is often modified for various stakeholder groups to focus on the most relevant information for a particular group It typically provides an overview of project objectives, timelines and milestones, team composition and key risks | Prepare and communicate to the project team and stakeholders about the project and to signal it is officially underway | O
M: Mandatory
A: Advised
O: Optional

## Slide 13: Issue Log and Risk Log are required to manage IM/IT projects
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Execute or Manage | 12 | Project Status Report | The Project Status Report is used to report periodic (weekly/bi-weekly or monthly) project progress and performance It includes an executive summary of the project status, project financials and key project metrics as well as a dashboard for change requests, risks and issues | Provides consistent information in specific cadence to keep project sponsor(s) and stakeholders informed To identify the need for additional support if/when issues arise | M
 | 13 | Issue Log | The Issue Log is a spreadsheet used to log, evaluate, monitor, control, and report project issues The Issue Log brings visibility and priority to project issues to facilitate their resolution | To document, track, manage and bring visibility to project issues | M
 | 14 | Risk Log | The Risk Log is a spreadsheet used to log, evaluate, monitor, control and report project risks The Risk Log brings visibility and priority to identify and then manage risks to increase positive events and decrease negative events | To document, track, manage and bring visibility to project risks | M
M: Mandatory
A: Advised
O: Optional

## Slide 14: Change Request Log and Project Status Report are mandatory documents for managing IM/IT projects
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Execute or Manage | 15 | Deliverable Overview and Acceptance Form | The Deliverable Overview and Acceptance Form serves two purposes: Define the requirements (criteria) for the successful completion of a deliverable Provide the process (i.e. who) for formally accepting and signing off a deliverable | This form establishes a consistent understanding of what is required and provides a record of that agreement Further, it expedites closure and approval of deliverables by explicitly identifying the success criteria (at the start), so both the project team and approver clearly understand the end goal(s) | M
 | 16 | Change Request Log | The Change Request Log is a spreadsheet used to log, analyze, and manage project change requests through the project's defined change control process | To manage and document the process of submitting and approving change requests Further, the log enables decisions made over time to be reviewed and impacts to the project baselines (scope, schedule or budget) to be identified | M
M: Mandatory
A: Advised
O: Optional

## Slide 15: Action Item Log and Decision Log are highly advised documents for managing IM/IT projects
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Execute or Manage | 17 | Action Item Log | The Action Item Log is a spreadsheet used to log, evaluate, execute, monitor, control, and close project action items | Having a designated log to manage action items assists to identify, prioritize, assign, monitor, and control action items throughout all phases of the project | A
 | 18 | Decision Log | The Decision Log is a spreadsheet used to capture, analyze, manage, monitor, and control day-to-day and formal project decisions | The log serves multiple purposes including: Document project decisions that may have scope, schedule or budget implications Provide insight into the rational, conditions or assumptions used for a decision at a point in time Provide a formal record for scope management and change control purposes | O
M: Mandatory
A: Advised
O: Optional

## Slide 16: Phase-end Review Checklist and Project Closure Report are optional documents for managing IM/IT projects
Project Phase | # | Tool Name | What is the tool? | Why is the tool used? | MAO?
Close | 19 | Phase-end Review Checklist and Project Closure Report | The Phase-end Review Report documents milestone accomplishments, risks and issues impacting the next phase, metric trends, process improvements, lessons learned, and other key findings over the course of a project phase. The Phase-end Review Report is used to communicate actions required by the project team to implement improvements for the project work going forward The Project Closure Report summarizes project closure activities and provides the final internal document of record for a project | Phase-end Review and Project Closure activities are required to confirm that all project and or phase objectives have been met and to perform important project and or phase closure activities | O
M: Mandatory
A: Advised
O: Optional

## Slide 17: Sample project management templates and checklists
The complete suite of IM/IT project management tools is available on IM/IT Capital Investment Branch’s intranet and SharePoint sites.